## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Brennan | Seth | Ishrak | Michael | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary & | Documentation |  |  |  |  | 24 |  | 20 |  |  |  |  | 0
Parallel Tasks |  | Project Charter | Project Manager, Developers | Seth, Brennan, Ishrak, Michael | 8 |  | 6 |  | 1.5 | 1.5 | 1.5 | 1.5 | 6
|  | Requirements Document | Project Manager, Developers | Seth, Brennan, Ishrak, Michael | 8 |  | 6 |  | 1.5 | 1.5 | 1.5 | 1.5 | 6
| Requirements |  |  |  |  | 8 |  | 8 |  |  |  |  | 0
|  | Gather | Project Manager, Developers | Seth, Brennan, Ishrak, Michael | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Analyze | Project Manager, Developers | Seth, Brennan, Ishrak, Michael | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Research | Development |  |  |  |  | 8.5 |  | 5
Iteration 1: |  | Preliminary Web Filtering Research | Developer | Michael | 2 |  | 1.5 |  |  |  |  | 1.5 | 1.5
|  | Preliminary Spam Detection Research | Developer | Michael | 2 |  | 0.5 |  |  |  |  | 0.5 | 0.5
|  | Preliminary Cybersecurity Research | Developer | Brennan | 2 |  | 1.5 |  | 1.5 |  |  |  | 1.5
|  | Preliminary Database Research | Developer | Ishrak | 2 |  | 1 |  |  |  | 1 |  | 1
| Documentation | [11 empty] | 0
|  | Iteration 1 Report | Developer | Ishrak | 0.5 |  | 0.5 |  |  |  | 0.5 |  | 0.5
Total |  |  |  |  | 32.5 | 40.5 | 25 | 33 | 6.5 | 5 | 6.5 | 7 | 25