## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Brennan | Seth | Ishrak | Michael | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary & | Documentation |  |  |  |  | 24 |  | 20 |  |  |  |  | 0
Parallel Tasks |  | Project Charter | Project Manager, Developers | Seth, Brennan, Ishrak, Michael | 8 |  | 6 |  | 1.5 | 1.5 | 1.5 | 1.5 | 6
|  | Requirements Document | Project Manager, Developers | Seth, Brennan, Ishrak, Michael | 8 |  | 6 |  | 1.5 | 1.5 | 1.5 | 1.5 | 6
| Requirements |  |  |  |  | 8 |  | 8 |  |  |  |  | 0
|  | Gather | Project Manager, Developers | Seth, Brennan, Ishrak, Michael | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Analyze | Project Manager, Developers | Seth, Brennan, Ishrak, Michael | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
0
0
Research | Development |  |  |  |  | 8.5 |  | 5
Iteration 1: |  | Preliminary Web Filtering Research | Developer | Michael | 2 |  | 1.5 |  |  |  |  | 1.5 | 1.5
|  | Preliminary Spam Detection Research | Developer | Michael | 2 |  | 0.5 |  |  |  |  | 0.5 | 0.5
|  | Preliminary Cybersecurity Research | Developer | Brennan | 2 |  | 1.5 |  | 1.5 |  |  |  | 1.5
|  | Preliminary Database Research | Developer | Ishrak | 2 |  | 1 |  |  |  | 1 |  | 1
| Documentation | [11 empty] | 0
|  | Iteration 1 Report | Developer | Ishrak | 0.5 |  | 0.5 |  |  |  | 0.5 |  | 0.5
0
0
0
Iteration 2: | Development |  |  |  |  | 5 |  | 8 |  |  |  |  | 0
|  | Cybersecurity Program Analysis | Developer | Brennan | 0.5 |  | 1 |  | 1 |  |  |  | 1
|  | Penetration Test Plan Development | Developer | Brennan | 0.5 |  | 1 |  | 1 |  |  |  | 1
|  | Web Filtering Research | Developer | Michael | 2 |  | 3 |  |  |  |  | 3 | 3
|  | Spam Detection Research | Developer | Michael | 2 |  | 3 |  |  |  |  | 3 | 3
0
0
| Documentation |  |  |  |  | 5 |  | 7 |  |  |  |  | 0
|  | Project Plan | Developers | Michael, Ishrak | 2 |  | 4 |  |  |  | 1 | 3 | 4
|  | Risk Management Report | Project Manager, Developer | Seth, Brennan | 2 |  | 2 |  | 1 | 1 |  |  | 2
|  | Iteration 2 Report | Developers | Ishrak | 1 |  | 1 |  |  |  | 1 |  | 1
Iteration 3: | Development |  |  |  |  | 7 |  | 10 |  |  |  |  | 0
|  | Web Filtering Research | Developer | Michael | 2 |  | 3 |  |  |  |  | 3 | 3
|  | Spam Detection Research | Developer | Michael | 2 |  | 3 |  |  |  |  | 3 | 3
|  | Penetration Test Research | Developer | Brennan | 2 |  | 2 |  | 2 |  |  |  | 2
|  | Database Research | Developer | Ishrak | 1 |  | 2 |  |  |  | 2 |  | 2
|  | Server Research | Developer | Ishrak | 1 |  | 1 |  |  |  | 1 |  | 1
0
0
0
0
| Documentation |  |  |  |  | 4 |  | 4 |  |  |  |  | 0
|  | Architecture | Developer | Brennan, Ishrak | 3 |  | 3 |  |  |  | 3 |  | 3
|  | Iteration 3 Report | Developer | Michael | 1 |  | 1 |  |  |  |  | 1 | 1
Iteration 4: | Development |  |  |  |  | 12 |  | 12 |  |  |  |  | 0
|  | Web Filtering Research | Developer | Michael | 2 |  | 2 |  |  |  |  | 1 | 1
|  | Spam Detection Research | Developer | Michael | 2 |  | 2 |  |  |  |  | 1 | 1
|  | Cybersecurity Research | Developer | Brennan | 2 |  | 2 |  | 1 |  |  |  | 1
|  | Database Research | Developer | Ishrak | 2 |  | 2 |  |  |  | 1 |  | 1
|  | Server Research | Developer | Ishrak | 2 |  | 2 |  |  |  | 1 |  | 1
|  | Network Research | Project Manager | Seth | 2 |  | 2 |  |  | 1 |  |  | 1
0
0
0
0
| Documentation |  |  |  |  | 1 |  | 1 |  |  |  |  | 0
|  | Iteration 4 Report | Developer | Ishrak | 1 |  | 1 |  |  |  | 1 |  | 1
0
Iteration 5: | Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
0
0
0
0
| Documentation |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
0
0
Total |  |  |  |  | 54.5 | 61.5 | 55 | 62 | 11.5 | 6 | 14.5 | 23 | 55